# L1 SignalFabric — Parallel Build & Daily Demo Plan

Layer: L1 SignalFabric

Engineers: Sreekumar M K, Sruthy

Window: Jun 08 → Jun 12, 2026 (daily demoable build)

Milestones: Prototype Jun 10 · Design + Test docs (async review) Jun 12 · Prod target Jun 15

Source folder: L1SignalFabric/ (new top-level module)

────────────────────────────────────────

## 1. Context & Goal

L1 SignalFabric is the continuous event-ingestion layer that feeds the L2 knowledge graph

(OrgMap + workflow nodes such as SignOffEvent). It extends the existing upstream

ingestion pattern from *batch snapshots* to *continuous streams*.

The upstream pipeline today ships file/batch adapters: SourceAdapter → FileExtractor (Phase 1), with

APIExtractor (Phase 2) and CDCExtractor (Phase 3) stubbed for the future. The Python

scrapers (Slack, Notion) pull history in batches and emit *.jsonl + manifest.json.

L1 SignalFabric realizes the Phase-3 event-stream vision: real-time push connectors

that emit the same canonical Record shape as continuous DELTA operations instead of

SNAPSHOT files.

### 1.1 Focus order (per request)

We build the three highest-value streams first. They map onto all five prototype sources:

| Focus area (build first) | Upstream source(s) covered | Feeds | Operation |
| --- | --- | --- | --- |
| 1. Slack Events API — real-time webhook push (messages, reactions, channel joins) | Slack | OrgMap *tribal knowledge* only | DELTA |
| 2. Gmail API (Workspace) — Pub/Sub push, metadata only (sender, recipient, thread, ts) | email sign-off events | OrgMap + SignOffEvent node in L2 | DELTA |
| 3. ERP Integration — CDC/outbox streaming | Crew DB · Contract (CLM) · Vessel/Port DB | L2 entities | DELTA |

Body content is never ingested for Gmail (metadata only). **No tool secrets or source

bodies enter any hosted container** — same boundary the managed-agents layer keeps

(`ARCHITECTURE.md` §0).

### 1.2 Exit criteria (the scoreboard)

☐ All 5 sources streaming (not batch)

☐ Sign-off email → L2 SignOffEvent node in < 5 min

☐ 50 crew records, 0 data loss

☐ Changes propagate downstream in < 5 min

────────────────────────────────────────

## 2. Target Architecture (what we build in L1SignalFabric/)

A standalone Python 3.12 / FastAPI service (matches the project stack in

`README.md`) that mirrors the upstream interface ladder, but as a

*push/stream* engine.

Figure 1 — L1 SignalFabric connector architecture: real-time push ingress → connector → normalizer → event bus → L2 sink (OrgMap + SignOffEvent).

### 2.1 Core abstractions (mirror the upstream pipeline)

`EventStreamConnector` — Phase-3 analogue of the upstream CDCExtractor:

subscribe(), verify(req), position() (resume watermark), emit() -> SignalEvent.

`SignalEvent` — canonical record, 1:1 with the upstream Record

(entity, key, sourceSystem, tenantId, data, operation=DELTA, timestamp,

extractedAt, lineage). Reusing the shape means L2/downstream stays batch-compatible.

`SourceSystem` — extends the upstream enum (SLACK, EMAIL already exist;

add CREW_DB, CONTRACT_CLM, VESSEL_PORT_DB under an ERP family).

`EventBus` — InMemoryBus (Day 1 demo) → RedisStreamsBus (Day 4, durable + replay).

`L2Sink` — idempotent upsert into OrgMap; special-cases sign-off emails into a

SignOffEvent node. At-least-once delivery + DLQ.

`CheckpointStore` — per-connector position for crash-safe resume (0 data loss).

### 2.2 Why a new service, not an edit to the upstream pipeline

L1 SignalFabric is built as a standalone module that vendors the contract (the

Record/SourceSystem shapes) into L1SignalFabric/core/ and keeps wire compatibility, so

the work can later be folded back upstream as its real Phase-3 CDCExtractor

implementations — without modifying the existing upstream codebase.

────────────────────────────────────────

## 3. Parallel Work Split

Two independent tracks with a stable seam = the `EventBus` + `SignalEvent` contract.

Track A owns everything *left* of the bus (ingress/connectors); Track B owns the bus

internals and everything *right* of it (normalize→sink→L2→observability). Either side can be

demoed against a mock on the other side, so neither blocks the other.

|  | Track A — Sreekumar (Ingress & Connectors) | Track B — Sruthy (Core, Sink & Observability) |
| --- | --- | --- |
| Owns | Slack Events receiver, ERP connector, connector framework, signature/verification, dedup | Event bus, normalizer, L2 sink + SignOffEvent, checkpoint/retry/DLQ, dashboard, test harness |
| Day 1 | Scaffold + EventStreamConnector iface + Slack & ERP skeletons + Slack URL-verify handshake | SignalEvent schema + InMemoryBus + L2Sink stub + SSE /stream + mock-event generator + docker-compose |
| Day 2 | Real Slack Events (signature verify, message/reaction/join, dedup by event_id) | Slack→OrgMap normalizer + OrgMap upsert + live OrgMap viewer + retry/DLQ |
| Day 3 | Sign-off email → SignOffEvent creation + latency instrumentation (<5 min) | Gmail Pub/Sub push endpoint + watch() + history.list metadata-only + thread/edge mapping |
| Day 4 | ERP CDC/outbox streaming (Crew/Vessel-Port/Contract) + 50-record load + 0-loss proof | RedisStreamsBus + CheckpointStore resume + per-source latency metrics + failure/retry suite |
| Day 5 | All-source live wiring + Slack/ERP test cases + Design-doc sections owned | Consolidated dashboard + full test suite run + Test-doc + Design-doc data-flow diagram |

Shared/agreed Day 1 (pair for 1 hr): lock SignalEvent JSON schema, bus interface,

and the /stream event envelope. Everything after keys off those.

────────────────────────────────────────

## 4. Day-by-Day Plan — each day a clean end-to-end demo

Demo rule: every day ends with make demo that runs green from a cold start and shows a

visible event traveling source → L2. No day depends on un-demoed scaffolding.

### Day 1 — Jun 08 (Mon): Skeleton end-to-end "first signal"

Goal: one synthetic event flows ingress → bus → normalizer → L2 store → live tail.

A (Sreekumar): repo scaffold under L1SignalFabric/; EventStreamConnector interface;

Slack + ERP connector skeletons; Slack url_verification challenge endpoint;

/healthz.

B (Sruthy): SignalEvent model (mirrors Record); InMemoryBus; L2Sink stub

(append-only JSONL + WebSocket/SSE broadcast); GET /stream (SSE live tail);

scripts/inject_mock.py (emits a fake Slack msg + fake email-metadata event);

docker-compose.yml + Makefile.

✅ Demo 1: make up && make demo → injected mock Slack message and mock email

metadata appear, normalized, in the L2 JSONL store and scroll live on the SSE dashboard.

Health check green. *(Proves the whole pipe with mocks.)*

────────────────────────────────────────

### Day 2 — Jun 09 (Tue): Slack Events API live

Goal: a real Slack action shows up in OrgMap within seconds.

A: Slack Events API receiver — X-Slack-Signature HMAC verification, handle

message, reaction_added, member_joined_channel; idempotent dedup on event_id;

Socket Mode fallback so the demo works without a public URL (or ngrok tunnel).

B: Slack→canonical normalizer (reuse the field shape from the existing Slack scraper model);

OrgMap upsert (person ↔ channel ↔ interaction edges = tribal knowledge); live OrgMap

viewer pane; retry + DLQ on sink failure.

✅ Demo 2: post a message, add a reaction, and join a channel in a test Slack workspace →

all three surface in the OrgMap viewer in real time, deduped, with retry shown on a forced

sink error. *(Slack source = streaming ✔)*

────────────────────────────────────────

### Day 3 — Jun 10 (Wed): Gmail metadata + SignOffEvent — PROTOTYPE MILESTONE

Goal: email metadata streams to OrgMap; a sign-off email auto-creates a SignOffEvent < 5 min.

B: Gmail push pipeline — users.watch() registration → Google Cloud Pub/Sub topic →

POST /gmail/push (JWT-verified) → history.list pulls metadata only

(from/to/cc, thread, timestamp — never body); map participants → OrgMap edges.

A: Sign-off detector → create SignOffEvent node in L2; end-to-end **latency

instrumentation** (extractedAt → sinkAt) with a <5-min SLO gauge; idempotency so a

re-delivered Pub/Sub message doesn't double-create.

✅ Demo 3 (Proto): send a normal email in the test Workspace → metadata edge appears in

OrgMap; send a sign-off email → a SignOffEvent node is created in L2 and the latency

gauge reads < 5 min. Slack still streaming alongside. *(Hits Jun-10 Proto + the sign-off

exit criterion.)*

────────────────────────────────────────

### Day 4 — Jun 11 (Thu): ERP Integration + durability

Goal: ERP changes stream as DELTAs; restart loses nothing; 50-record load is clean.

A: ERP connector covering Crew DB · Vessel/Port DB · Contract (CLM) via CDC/outbox

pattern (watermark on updated_at or an outbox table) emitting DELTA records — the

real Phase-3 CDCExtractor shape. Seed + drive 50 crew records; prove 0 data loss.

B: swap InMemoryBus → `RedisStreamsBus` (durable, replayable); `CheckpointStore`

so a connector resumes from last position after a kill; per-source latency dashboard;

failure/retry test suite (drop, restart, duplicate, poison message → DLQ).

✅ Demo 4: update a crew row → DELTA reaches L2 < 5 min; kill a connector mid-stream

and restart → it resumes with 0 lost / 0 duplicated records; run the 50-record batch →

count reconciles exactly. *(All 5 sources now streaming ✔)*

────────────────────────────────────────

### Day 5 — Jun 12 (Fri): Full E2E hardening + docs — DESIGN & TEST DOCS DUE

Goal: everything streaming at once; tests pass live; docs ready for async review.

A + B together: run Slack + Gmail + ERP simultaneously into one consolidated dashboard;

finalize the Design doc (connector architecture, stream schema, upstream-extension

approach, data-flow diagram) and Test doc (50-record ingestion, per-source latency,

sign-off trigger, failure/retry).

✅ Demo 5 (final): full live end-to-end — real Slack action, real email metadata + a

sign-off → SignOffEvent, and an ERP crew update, all landing in L2 < 5 min on one screen;

then run the test suite live (50-record, latency, sign-off, failure/retry) — all green.

────────────────────────────────────────

## 5. Demo Safety Net (so every day is "perfectly showable")

| Risk | Mitigation kept ready each day |
| --- | --- |
| No public URL for Slack/Gmail webhooks | Socket Mode (Slack) + ngrok/Cloud Run tunnel; scripts/replay.py replays captured real payloads |
| Google Workspace / Pub/Sub not provisioned in time | Pub/Sub emulator + recorded push payloads; same /gmail/push code path |
| Live Slack workspace unavailable | recorded event_id-stamped fixtures under fixtures/ |
| ERP DB not ready | local Postgres (already in stack) seeded with 50 crew rows + outbox table |
| Flaky network during demo | every connector has a fixture/replay mode; make demo defaults to a deterministic path, make demo-live for real sources |

Each demo is driven by a single make demo-dayN target committed the same day, so a cold

checkout reproduces it.

────────────────────────────────────────

## 6. Deliverables checklist (Due Jun 12, async review)

Design doc — connector architecture · SignalEvent stream schema · upstream-extension

approach (Phase-3 CDCExtractor) · data-flow diagram.

Test doc — 50-record ingestion test · latency test per source · sign-off trigger test ·

failure/retry scenarios.

Code (`L1SignalFabric/`): core contracts, 3 connectors (Slack/Gmail/ERP), event bus

(in-mem + Redis), L2 sink + SignOffEvent, checkpoint/DLQ, dashboard, make demo-day1..5,

test suite.

────────────────────────────────────────

## 7. Definition of Done (per exit criteria)

| Exit criterion | Proven by | Day |
| --- | --- | --- |
| All 5 sources streaming (not batch) | Day-5 consolidated live demo | 5 |
| Sign-off email → L2 node < 5 min | Day-3 SignOffEvent + latency gauge | 3 |
| 50 crew records, 0 data loss | Day-4 load + reconciliation | 4 |
| Changes propagate downstream < 5 min | Day-4 per-source latency dashboard | 4 |

</content>